## timeplan
|  | Day | 7. April 2026 | [7 empty] | 8. April 2026 | [7 empty] | 9. April 2026 | [7 empty] | 10. April 2026 | [7 empty] | 14. April 2026 | [7 empty] | 15. April 2026 | [7 empty] | 16. April 2026 | [7 empty] | 17. April 2026 | [7 empty] | 21. April 2026 | [7 empty] | 22. April 2026
|  | Hour | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
# | Type | Task / Activity
Create repository and setup code base (Planned) | bar: 7. April 2026 1 to 22. April 2026 8
(Actual) | bar: 7. April 2026 1 to 22. April 2026 8
| Setup | Start PostgreSQL in a Podman container and verify connection with Backend | bar: 7. April 2026 1 to 22. April 2026 8
[5 empty] | 1 | 1
I | Inform | Start documenting "inform" section of IPERKA | bar: 7. April 2026 1 to 22. April 2026 8
[7 empty] | 1 | 1
I | Inform | Create ERD, document the work so far and write journal | bar: 7. April 2026 1 to 22. April 2026 8
[9 empty] | 1 | 1
P | Plan | Create 2 mock-ups for the frontend UI design (figma) | bar: 7. April 2026 1 to 22. April 2026 8
[11 empty] | 1 | 1 | 1 | 1
P | Plan | Draft frontend and backend application structure (figma) | bar: 7. April 2026 1 to 22. April 2026 8
[15 empty] | 1 | 1
P | Plan | Have expert meeting and do analysis/reflection | bar: 7. April 2026 1 to 22. April 2026 8
[17 empty] | 1 | 1
I | Inform | Document project requirements based on "inform" section | bar: 7. April 2026 1 to 22. April 2026 8
[19 empty] | 1 | 1
P | Plan | Document implementation concept based on application structure draft | bar: 7. April 2026 1 to 22. April 2026 8
[21 empty] | 1 | 1
P | Plan | Write test concept based on implementation concept | bar: 7. April 2026 1 to 22. April 2026 8
P | Plan | Document "plan" section and write journal | bar: 7. April 2026 1 to 22. April 2026 8
[23 empty] | 1 | 1 | 1 | 1 | 1
E | Decide | Document solution variants | bar: 7. April 2026 1 to 22. April 2026 8
[28 empty] | 1 | 1 | 1
E | Decide | Compare solution variants based on a pros vs cons | bar: 7. April 2026 1 to 22. April 2026 8
[31 empty] | 1 | 1
E | Decide | Write decision justifications | bar: 7. April 2026 1 to 22. April 2026 8
1
E | Decide | Document "decide" section and write journal | bar: 7. April 2026 1 to 22. April 2026 8
1
R | Realise | Implement backend entities and its relations | bar: 7. April 2026 1 to 22. April 2026 8
1
R | Realise | Implement backend CRUD operations | bar: 7. April 2026 1 to 22. April 2026 8
[36 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
R | Realise | Verify data retrieval from backend from frontend | bar: 7. April 2026 1 to 22. April 2026 8
[43 empty] | 1 | 1
R | Realise | Create frontend services | bar: 7. April 2026 1 to 22. April 2026 8
[49 empty] | 1 | 1
R | Realise | Manually test endpoints and document problems | bar: 7. April 2026 1 to 22. April 2026 8
[45 empty] | 1 | 1 | 1 | 1
R | Realise | Build frontend UI layout | bar: 7. April 2026 1 to 22. April 2026 8
[53 empty] | 1 | 1 | 1 | 1 | 1 | 1
R | Realise | Implement frontend functionalities | bar: 7. April 2026 1 to 22. April 2026 8
[51 empty] | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
C | Control | Write frontend tests | bar: 7. April 2026 1 to 22. April 2026 8
C | Control | Write backend tests | bar: 7. April 2026 1 to 22. April 2026 8
R/C | Realise + Control | Document "realisation" and "control" section | bar: 7. April 2026 1 to 22. April 2026 8
[67 empty] | 1 | 1 | 1 | 1
A | Evaulate | Compare realisation against requirements | bar: 7. April 2026 1 to 22. April 2026 8
[71 empty] | 1 | 1 | 1 | 1
A | Evaulate | Evaluate planned objectives against achieved objectives | bar: 7. April 2026 1 to 22. April 2026 8
[75 empty] | 1 | 1 | 1 | 1
A | Evaulate | Document "evaluation" section | bar: 7. April 2026 1 to 22. April 2026 8
[79 empty] | 1 | 1
A | Evaulate | Finalise and hand in project | bar: 7. April 2026 1 to 22. April 2026 8
[81 empty] | 1 | 1